## Sheet1
Activity ID | Activity Description | Estimated Duration (Days) | Preceding Activities | Activity Owner
A1 | Establish Project Timeline and Schedule | 3 days | - | Project Manager
A2 | Allocate Resources to Project Tasks | 2 days | A1 | Project Manager
A3 | Track Actual vs. Planned Expenditure | 1 days | A2 | Project Manager
A4 | Establish Communication Channels | 2 days | A1 | Project Manager
A5 | Prioritize Requirements | 1 days | A1 | Business Analyst
A6 | Design System Integration Approach | 2 days | A5 | System Analyst
A7 | Define Visual Style Guide | 3 days | A5 | UI/UX Designer
A8 | Set Up Backend Framework | 4 days | A6 | Backend Developer
A9 | Design Database Schema | 5 days | A6 | Backend Developer
A10 | Integrate Backend Registration Endpoint | 3 days | A8,A9 | Backend Developer
A11 | Test User Registration Workflow | 3 days | A10 | QA Tester
A12 | Implement Activity Input Interface | 5 days | A7,A10 | Frontend Developer
A13 | Implement Calorie Calculation Engine Backend & Frontend | 7 days | A8,A9,A12 | Backend Developer / Frontend Developer
A14 | Implement Meal Input Interface | 5 days | A7,A12 | Frontend Developer
A15 | Define Testing Scope and Objectives | 1 days | A11,A13,A14 | QA Tester
A16 | Execute Functional Tests | 3 days | A15 | QA Tester
A17 | Set Up UAT Testing Environment | 4 days | A16 | QA Tester
A18 | Deploy Application to Target Environment | 7 days | A17 | System Administrator
A19 | Implement Alerting Mechanisms | 6 days | A13,A18 | Backend Developer
A20 | Prepare Final Project Report | 2 days | A18,A19 | Project Manager